## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
COMP3000
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Harry Ormandy
Project start date: | 2024-09-30 |  |  |  |  | October | [27 empty] | November
Scrolling increment: | 5 | time axis 2024-10-05 to 2024-11-29
Milestone description | Category | Assigned to(Harry) | Progress | Start | Days | time axis 2024-10-05 to 2024-11-29
Project Planning and research | Goal
Project Initiation | On Track | Harry | 100% | 2024-09-30 | 10
research and shortlist of OSINT tools to implement | On Track | Harry | 100% | 2024-10-10 | 5
requirements abstraction and user story mapping | On Track | Harry | 100% | 2024-10-15 | 5
Legal, Social, Ethical and Professional considerations | On Track | Harry | 100% | 2024-10-20 | 10
Low fidelity prototyping | On Track | Harry | 100% | 2024-10-30 | 10
Sprint Overrun | Low Risk | Harry | 100% | 2024-11-09 | 15
Development phase 1: Project Setup and MVP | Goal
Django Template setup | On Track | Harry | 100% | 2024-11-28 | 5
API implementation test | On Track | Harry | 100% | 2024-12-05 | 10
Login and registration page templates | On Track | Harry | 100% | 2025-01-09 | 5
Login, Registration form creation with database | On Track | Harry | 100% | 2025-01-14 | 5
hard coded main page and settings menu | On Track | Harry | 100% | 2025-01-19 | 5
Development Phase 2: Advanced features and APIs, interface design | Goal
data forms database added | On Track | Harry | 100% | 2025-01-26 | 2
News API section with scroll view | On Track | Harry | 100% | 2025-01-28 | 2
Settings menu links | On Track | Harry | 100% | 2025-01-30 | 2
News API to use database | On Track | Harry | 100% | 2025-02-01 | 4
Tabs for different data sources | On Track | Harry | 100% | 2025-02-05 | 2
Development Phase 3: OSINT and data integration | Goal
Add Twitter API | On Track | Harry | 100% | 2025-02-08 | 2
Add Github API | On Track | Harry | 100% | 2025-02-10 | 2
Add Reddit API | On Track | Harry | 100% | 2025-02-12 | 2
Add Data breach API | On Track | Harry | 100% | 2025-02-14 | 2
Add facebook API | High Risk | Harry | 100% | 2025-02-16 | 2
Create Hints database | On Track | Harry | 100% | 2025-02-18 | 2
Create scoring algorithm | On Track | Harry | 100% | 2025-02-20 | 2
Sprint overrun | Low Risk | Harry | 100% | 2025-02-22 | 10
Development Phase 4: Template Management and Dynamic Views | Goal
confirmed results database | On Track | Harry | 100% | 2025-03-03 | 2
dynamic results page | On Track | Harry | 100% | 2025-03-05 | 3
dynamic scoring algorithm | On Track | Harry | 100% | 2025-03-08 | 2
dynamic hints display | On Track | Harry | 100% | 2025-03-10 | 3
Sprint Overrun | Low Risk | Harry | 100% | 2025-03-13 | 5
Development Phase 5: Final product development and Pre-testing
unit Testing | On Track | Harry | 100% | 2025-03-18 | 3
bug fixing | On Track | Harry | 100% | 2025-03-21 | 2
User acceptance Testing | On Track | Harry | 100% | 2025-03-23 | 5
Feature alteration | On Track | Harry | 100% | 2025-03-28 | 5
Final bug fixing | On Track | Harry | 100% | 2025-04-02 | 2
To add more data, Insert new rows ABOVE this one