## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
COMP3000
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Harry Ormandy
Project start date: | 2024-09-30 |  |  |  |  | October | [27 empty] | November
Scrolling increment: | 5 | time axis 2024-10-05 to 2024-11-29
Milestone description | Category | Assigned to(Harry) | Progress | Start | Days | time axis 2024-10-05 to 2024-11-29
Project Planning
Project Initiation | On Track |  | 100% | 2024-10-08 | 2
requirements abstraction and user story mapping | Low Risk |  | 0% | 2024-10-13 | 5
research and shortlist of OSINT tools to implement | Low Risk |  | 0% | 2024-10-21 | 2
Legal, Social, Ethical and Professional considerations | Low Risk |  | 0% | 2024-10-23 | 2
Low fidelity prototyping | Low Risk |  | 0% | 2024-10-28 | 5
Development phase 1: MVP
Basic GUI creation in Python | Low Risk |  | 0% | 2024-11-04 | 5
implementation of basic OSINT api's | Low Risk |  | 0% | 2024-11-11 | 5
Displaying OSINT harvested data to the user | Low Risk |  | 0% | 2024-11-16 | 14
implementing hardcoded tips section | Low Risk |  | 0% | 2024-12-02 | 3
Bug fixing | Low Risk |  | 0% | 2024-12-05 | 2
Sprint Overrun | Low Risk |  | 0% | 2024-12-09 | 5
Development Phase 2: footprint calculation
Development Phase 3: accounts and footprint score persistence
Development Phase 4: Ensuring Legal and ethical compliance
Development Phase 5: Final product development
unit Testing
User acceptance Testing
Bug fixing
To add more data, Insert new rows ABOVE this one